## Testing Status
Pilot User | Expected Information | Prompt / Query | Actual Output | Categorization | Will it be Implemented ? (Inputs from the Usecase owner) Reckemeyer Luca (QM DI AID) | Will it be implemented ? (Alignment with IT) | Implementation Status | IT Implementation comments
Andreas Kienel (QM PMT) | For case 800025699010: This is a valid number, but for an internal complaint. With it I wanted to check if QUAI will count them as a complaint (which he should not do) But instead the “endless loading” happened. Expected results from QUAI: Something like: “This is not a valid ID for a technical customer complaint” | What is the product from case 800025699010 | Endless loading | System bugs | yes | yes | completed | fixed, new reply """ I searched for the case/CMA number 800025699010 (exactly as you wrote it) to find the associated product, but no records were found for “case 800025699010” in the SQL results available to me. Please double-check the identifier you provided as the search filter: • Confirm the CMA/case number is correct (all digits, no missing/extra digits), or try searching with a different identifier tied to the case such as the MA Number or the product/sales name (if you have it). Also, note: • SAR cases are excluded from this search. If this might be a SAR case, tell me and I can try including SAR cases. • PL 57 cases are excluded from this search. If you want PL 57 included, let me know.""" (https://quai-deploy-web-uat-quai-development.ap-sg-1.icp.infineon.com/share/caed2628-8bef-4bb1-8313-5362d067348a)
Andreas Kienel (QM PMT) | 2 | Can you provide a list of cases for product IDP30E120? | Endless loading | System bugs | yes | yes | completed | Update: all are SARs cases, so get this new reply """ I searched for records using the exact identifier you provided: CMA number 800213341010 (12-digit case identifier). No records were found that match 800213341010. Please double-check the value you want to use as the search filter (the identifier entered in the query), or try an alternative identifier if you have one, such as: • CMA/case Number (confirm all digits are correct; no missing/extra digits) • MA Number • Product/Sales name Also note: SAR cases and PL 57 cases were excluded from this search. If your case might be a SAR or PL 57 case, tell me and I can rerun the search including those.""" if asked to include SARs, will get """Included SAR case details for CMA 800213341010 (1 distinct case)"""
Andreas Kienel (QM PMT) | Not 0, Same results for "No Trouble Found", "EOS" or "Electrical overstress" | How many complaints were closed as NTF in 2026? | 0 | Enhancements (additional data required, Logic Revisements) | yes | yes | in progress | ADM_COMPLETION_DATE added, got 822 Jiang Yixin (IT SBI BIA CCA / External) Pls check again -- will update once got all the root cause desc fields
Andreas Kienel (QM PMT) | The data "Customer Region" should be included. | "How many complaints did we receive from customer Bosch? --> Correct results Follow-up questions: Can you differentiate the number of complaints to the regions?" | not able to provide | Enhancements (additional data required) | yes | yes | completed | "Region"" added, new response ""For complainer name matching “BOSCH”, the number of complaints by region is: Region Complaint Count ASIA/PACIFIC (WITHOUT JAPAN) 1012 GERMANY 638 EUROPE (WITHOUT GERMANY) - OUT 514 Emerging Markets 264 AMERICA (NAFTA) 257 EUROPE (WITHOUT GERMANY) - PAR 144 OTHER REGIONS (ROW) 8 """
Andreas Kienel (QM PMT) | 2 | How many complaints do we had from customer Diehl in 2026? | Same results for 2025 and 2026 - both wrong. I belive the bot is using the production data code. | Enhancements (additional data required) | yes | yes | completed | ADM_COMPLETION_DATE added, there is a one new case completed in June 2026, in total we have 3 case now
Andreas Kienel (QM PMT) | ~14 days | What was the average TAT in 2015 in the region Greater China? | not able to provide | Enhancements (additional data required) and System bugs | yes | yes | in progress | TAT and region added, and used ADM_COMPLETION_DATE to count the cases, but no region matched 'China', should also select country? [Screenshot: see "Screenshots" sheet, Image 1]
Pei Phoebe (PSS QM GC SHA) | cases list with CMA# | Is there any non-ESD/EOS and non-NTF cases for IPP039N10N5 ? | the case listed is NTF case, not the non-NTF case. | Enhancements (Logic Revisements) | yes | yes | in progress | root cause desc is used to filter non-ESD/EOS and non-NTF cases, user suggested using PSI_ITEM_KEYWORD -- AS-ls: only use root cause description to determine root cause, pending to include all levels root cause into consideration. Need to discuss how to determine the NON/NOT cases as well.
Suharni | "no data provided on the customers and regions Korea, AP , China, India" | continue ... who are the customers & region? previous question: How many complaints are raised by the various customers for the products SLE956681-0007 TSNP6 and what are the root causes since mass productions? | Data is out of scope. However, I can provide the closest available fields: Complainer name (as a proxy for customer) and Complainer country (as a proxy for region) if that would be helpful. | System bugs | yes | yes | completed | Text2sql tool tried to identify an attribute for mass production -- fixed, but noted that mass production date is not provided in far agent. -- new reply "Customers and region (for SLE956681-0007 / TSNP6, complaint key CAR): • AVNET ASIA PTE LTD — ASIA/PACIFIC (WITHOUT JAPAN) • AVNET TECHNOLOGY HONG KONG LIMITED — ASIA/PACIFIC (WITHOUT JAPAN)"
Li Kevin (PSS QM GC) |  | For product ISC018N08NM6, pls show me the global FAR history overview, any confirmed valid IFX caused issue? | Endless loading... | System bugs | yes | yes | in progress | -- endless loading bug fix. will update the final resply once all root cause owner levels added
Hussein Mohammed Reza (BE QM QEX) | 12 FARs but the answer was zero. | How many FARs do we received for LQFP-176? | 0 | Enhancements (additional data required) | yes | yes | completed | package name added, get 650 far cases, for the following package names: • PG-LQFP-176-14 • PG-LQFP-176-20 • PG-LQFP-176-22 • PG-LQFP-176-5 • PG-LQFP-176-9
Hussein Mohammed Reza (BE QM QEX) | 43 FARs but the answer was zero (For package PG-VQFN-48-31, the total number of FARs received is 0.) | How many FARs do we received for PG-VQFN-48-31? | 0 | Enhancements (additional data required) | yes | yes | completed | new reply """For package PG-VQFN-48-31, the total number of FARs received is 1470."""
Johanna Ocklenburg | The exact number of registered SAK-TC377TP-96F300S AA FARs in APril 2026 | How many FARs of SAK-TC377TP-96F300S AA were registered in April 2026? | For product SAK-TC377TP-96F300S AA in the period 2026-04-01 ? 2026-04-30, there were 0 FARs registered. | Enhancements (additional data required) | yes | yes | completed | register date added
Johanna Ocklenburg | 10/11/2025 | When was the internal closing date of case 825090980? | It showed me over and over the date codes of the FAR devices, which is not a case clsoing date. Die von dir gesuchten Datenfelder („Fall geschlossen“ / „int complete date“) liegen außerhalb des verfügbaren Datenumfangs. Allerdings könnte ich dir z.B. das Beschwerde-Eröffnungsdatum oder den aktuellen User-Status nennen, falls das hilft https://quai-deploy-web-uat-quai-development.ap-sg-1.icp.infineon.com/chat/38091ae4-310b-4ff0-9a43-93edaa3dfd83 | Enhancements (additional data required) | yes | yes | completed | closing date added, new response: For case 825090980, the internal closing date (administration completion date) was 2025-10-11.
Johanna Ocklenburg | Only cases for device TLE4998P3C | Show me all FAR cases of TLE4998P3C. The case starting date needs to be in the last 6 months. PSI item key word needs to start with ATV_RDD_FE. Show me the FAR case numbers, the customer name, PSI item keyword, sales description and the root cause owner coding in a table | Instead showing me cases from very different sales descriptions e.g SAL-TC270TP-64F200N DC https://quai-deploy-web-uat-quai-development.ap-sg-1.icp.infineon.com/chat/38091ae4-310b-4ff0-9a43-93edaa3dfd83 | Enhancements (additional data required) | yes | yes | completed | Starting date added, only cases for device TLE4998P3C provided.
Huang Ying (CSS OP QM 1) | show detailed corrective action of this case | what is the corrective action for this case CMA 826020727, sales name CY8C4245LQI-483, MA005768441 | not able to provide | Enhancements (additional data required) | yes | yes | completed | corrective action field added. new reply """ For CMA 826020727 (Sales Name CY8C4245LQI-483, MA Number MA005768441), the corrective action is: • Evaluate and define bond Z level tolerance Resp. ASEPH/Tel B."""
Huang Ying (CSS OP QM 1) | "show the correct SAR number of this part . For example: we have Case 826030951 & 826050013" | How many SARs in total for VSTD1313 WLB16? | not able to provide | Enhancements (additional data required) and Data Discrepancy (data missing) | yes | yes | in progress | add NN_COMPLAINT_KEY for CAR and SAR, but got data missing issue: not data of VSTD1313 WLB16 in dive, Data missing issue was reported to the CMA dive AO
Andreas Kienel (QM PMT) | ~7400 FAR | How many FARs did we had in 2026? | not able to provide | Enhancements (additional data required) and Data Discrepancy (data missing) | yes | yes | completed | ADM_COMPLETION_DATE added, got 7207 cases (distinct 9-digit CMA #)
Johanna Ocklenburg | A FAR list from the last two years for the product SAK-TC397XP-256F300S | Give me all FARs with corresponding lot number for the product SAK-TC397XP-256F300S from the last two years |  | Enhancements (Logic Revisements) | yes | yes | completed | used ADM_COMPLETION_DATE to get far cases
Stumer Robert | only RC for occurrence was provided | root casue ofr CMA 826030153001 | For CMA 826030153001, the identified root cause is: Metal. | Enhancements (Logic Revisements) | yes | Open | in progress | add PSI item keyword for Root Cause → Luca: PSI item keyword information is not expected for this question. The Problem was that only occurence and no escape root cause was given. For more details see Business logic requirements. -- AS-IS: pending to add escape root case (1-5 levels)
Abd Aziz Nur Suhaili | 7 cases | please help to list down all the FAR case from 2022 until now for sales code TLE9879QXH40 | "6 cases (exclude latest case 826040810) https://quai-deploy-web-uat-quai-development.ap-sg-1.icp.infineon.com/share/e486c61d-b932-4076-8820-0df67be6ec21" | Enhancements (Logic Revisements) | yes | yes | completed | used ADM_COMPLETION_DATE to get far cases
Pralhad Kulkarni | When I downloaded the source, actual is coming 4 , but in the query promt its showing 3 | Do we have any FAR reported for PL80 in 2026 ? | 3 | Enhancements (Logic Revisements) | yes | yes | completed | used ADM_COMPLETION_DATE to get far cases
Pralhad Kulkarni | 8 FARS | How many FAR reported in 2026 for PL81 ? | It listed 5, however the data source had 8 FARS listed. | Enhancements (Logic Revisements) | yes | yes | completed | checking with user on which date time to use
Andreas Kienel (QM PMT) | List of 16 cases "Product is from PL 57 (BIPOLAR), which should not be refelected Even if; too less cases are reflected" | For product TZ425N16KOF, the CMA numbers for complaints are: | For product TZ425N16KOF, the CMA numbers for complaints are: • 800219304010 • 822090827001 • 823090592001 • 824040620001 • 824120179001 • 825010865001 • 825090373001 | Enhancements (Logic Revisements) | yes | yes | completed | exclude PL 57, but got no result, all cases in db are PL 57 (confirmed with user, not data discrepance) -- updated, new reply "I searched for complaint records where the product name = “TZ425N16KOF” and tried to return the CMA numbers for those complaints, but no records were found matching “TZ425N16KOF”. Please double-check the identifier used as the search filter: Product name: confirm the exact spelling/format (e.g., any hyphens, spaces, suffixes, or alternate product/sales name) Also note: SAR cases were excluded from this search. If you want SAR included, tell me to include SAR cases. PL 57 cases were excluded from this search. If you want PL 57 included, tell me to include PL 57 cases. If you can share an alternate identifier (e.g., MA Number) associated with TZ425N16KOF, I can search using that as well"
Pei Phoebe (PSS QM GC SHA) | TAT for 826050065 is 8.92 | What's the TAT for 826050065 | the feedback is no this case in system | Enhancements (Logic Revisements) and Data Discrepancy (data missing) | yes | yes | completed | TAT added, but new response "For complaint 826050065, the TAT (turnaround time) is 16.65 days (value from system: 16.654594907407407).", pending to check -- update: TAT rounds to the nearest integer
Choy Wai Meng (ATV QM CQS CQM AP) | breakdown count for each sub-category, use PHA360 tool for clearer illustration | What are the FAR history for TLE75008-ESD for the past 3 years ? | not the expected format | Enhancements (output formatting) | yes | no | completed | The response formatting require pre-defined template to design the response. For break-down count to each category, you can extend the questions, i.e. What are the FAR history for TLE75008-ESD for the past 3 years and show the rootcause category with count..
Pei Phoebe (PSS QM GC SHA) | cases list with CMA# | how many CMA cases for end customer Delta//Google? | The data "End Customer" should be included. | Enhancements (output formatting) | yes | No further action required | No further action required | updated
Huang Ying (CSS OP QM 1) | A multi-line message is accepted and displayed correctly in the conversation. | " In the message box, press Ctrl+Enter to insert a new line" | Ctrl+Enter no function, does not work , No new line can be inserted | No Further Action Required | yes | No Further Action Required | No further action required | shift+Enter to insert a new line
Pralhad Kulkarni |  | what is the the number of impacted quantity in the month of Jun 2026 for PL80 ? | Taking too much time to process | No Further Action Required | no | No Further Action Required | No further action required | can not replicate this issue
Huang Ying (CSS OP QM 1) | " Existing feedback is removed or toggled off cleanly, with no duplicate state" | " Click the same Like or Dislike action again on the same response." | Does not work, Clicking the same like again will withdraw the Like , but will clean the previous feedback | No Further Action Required (to be discussed) | yes | No Further Action Required | No further action required | click 'like' once and click 'like' again will withdraw the like
Choy Wai Meng (ATV QM CQS CQM AP) | FA lab location | Which FA lab location to ship the FAR sample for TLE75008-ESD ? | not able to provide | Out of Scope | no | out of scope | Open | Incoming location from CMA ?
Maggie Chen | data source: CMA# list with CI inform | can you add customer interface name in the data source for each case? | no answer | Out of Scope | no | out of scope (PII) | No further action required | PII
Abd Aziz Nur Suhaili | "Ba Yuffie (ATV QM CQS CQM GC AQM) - Customer Interface Abd Aziz Nur Suhaili (ATV QM CQS ACM VIL) - Complaint Manager" | please provide the Customer Interface and Complaint Manager name for case 826041015 | "The data you are looking for is out of scope. However, I can provide the complainer name and cause owner description if that would be helpful. https://quai-deploy-web-uat-quai-development.ap-sg-1.icp.infineon.com/share/b9401d8d-11ed-4766-9e19-48cf64a1889e" | Out of Scope (data not provided) | no | out of scope (PII) | No further action required | PII
Stumer Robert |  | root casue for CMA 826030847 | not able to provide | Enhancements (Logic Revisements) | yes | yes | completed | CMA number normalization
Stumer Robert | have all CMA listed | CMA cases for IIPC63S4N08 | missed to provide all avaiallbe CMAs and at a certain point after I tried to chalange the bot, I received the message that I need to change to FAR bot, even if I already using it | No further action needed | yes | No further action required | No further action required | can't replicate this error, will keep tracking
Cabuhat Cynthia (PSS QM QES) | " No answer from QUAI. Expected answer: The status of CMA 82XXXXXXX or 82XXXXXXX is Status: ""Released"" " | "What is the current status of 826050141? What is the current status of CMA 826050141?" | not able to provide | Enhancements (Logic Revisements) | yes | yes | completed | CMA number format
Cabuhat Cynthia (PSS QM QES) | " No answer from QUAI. Expected answer: FAR (Failure Analysis Request); offiical Customer complaint SAR (Special Analysis Request); not official complaint; special analysis support provided" | " What is FAR? What is SAR? What is the difference between FAR and SAR ? What is the difference between SAR and FAR?" | not able to provide | Out of scope | yes | yes | Open | FAQ is not part of our current data scope, semantic search will be the solution to provide those general knowledge. TBD - Include intranet search for the FAQ related topics for next phase.
Andreas Kienel (QM PMT) | ~82% | What is the ratio of customer owned cases to Infineon owned case? | not able to provide | Enhancements (Logic Revisements) | yes | yes | completed | fixed, new response " For the cases in your query, the ratio of customer-owned to Infineon-owned cases is: • Customer-owned : Infineon-owned ≈ 50,380 : 10,679 • Simplified ratio ≈ 4.7 : 1 (customer : Infineon) Data used: • Customer cases: 50,380 • Infineon (IFX) cases: 10,679"
Maggie Chen | CMA# 826020493 | "BGA 824N6 E6329, any history sticky tape issue? any history case of sticky tape for PSS products? what about chipset stick on the film for PSS product?" |  | Enhancements (Logic Revisements) | yes | yes | in progress | As-ls: Check root cause description first and if not able to find, LLM may search across the PSI failure description. Action items: However, need clear definition regarding when and how to use few descriptive fields, i.e different levels of root cause, PSI failure descriptions, PSI item keywords etc. Note: Rajadurai Sudhan (IT SBI BIA CCA / External) Chipset stick on the film become chipset stuck on the film in the memory agent
Maggie Chen | 26 | Follow-up question: how many of them are from customer Delta Thailand? Previous question: pls list all CMA# of XDPP1100-Q024? | no records found | No further action required | No further action required | No further action required | No further action required | fixed, but got 24 cases, checkiing this data mismatching issue with user Jiang Yixin (IT SBI BIA CCA / External) how the response is generated? -- it is a follow-up query, the previous one is "pls list all CMA# of XDPP1100-Q024?"
Maggie Chen | Root cause | what is the root cause for CMA# 826020493? | no records found | Enhancements (Logic Revisements) | yes | yes | completed | "fixed, generate sql for 9-charactors cma #, new response """"""For CMA# 826020493, the identified root cause is “inline control.” """""""
Pei Phoebe (PSS QM GC SHA) | status is released | what's the status of CMA 826050819? | the feedback is no this case in system | Enhancements (Logic Revisements) | yes | yes | completed | fixed
Second Phase of Pilot Users 05 Aug 2026
Kim Yun Wen Rebecca (BE QM MP SIN QED) | There are 0 FAR cases from BE SIN (based on the cause owner description level 1 filter) for FY2526 year to date. | how many FAR from BE SIN? | https://quai-deploy-web-uat-quai-development.ap-sg-1.icp.infineon.com/share/e3a71ec7-c120-4535-8b7a-d83a8ff3c265 | Enhancement | yes |  |  | User: Would be good if chatbot ask user to clarify interested time period if user does not include time of interest
Kim Yun Wen Rebecca (BE QM MP SIN QED) | For FY2425, the total number of FAR cases (Cause Owner Desc Level 1 contains "BE SIN", CAR complaints, excluding Product Line 57) is 2. With summary table and link to datasource. | follow-up from TC-001: for FY2425? | https://quai-deploy-web-uat-quai-development.ap-sg-1.icp.infineon.com/share/e3a71ec7-c120-4535-8b7a-d83a8ff3c265 | Systerm bug? | yes
Kim Yun Wen Rebecca (BE QM MP SIN QED) | Yes. For Backend (Singapore) in FY2425 (including CAR and SAR), there are 2 distinct customer complaint cases. With summary table and link to datasource. | is there any customer complaint for backend singapore for FY2425? include CAR and SAR | https://quai-deploy-web-uat-quai-development.ap-sg-1.icp.infineon.com/share/ead0de5c-0f55-4388-9492-f044d97b08fe | System Bug | yes |  |  | User: There should be only 2 FAR cases for BE SIN for FY2425. The 2 cases are included in the list of 9 cases in the returned response but not sure why is there 7 others. The 2 cases are by Arrow Electronics and Hyundai Kefico
Patena Edwin Nalupa (BE QM MAL CQE 1) | Provide count of >1 case | FAR count cases For package PG-VQFN-48-31 | https://quai-deploy-web-uat-quai-development.ap-sg-1.icp.infineon.com/chat/5fc02a1b-f88f-474d-9592-02b4d7e20451 | System Bug? | yes |  |  | Reckemeyer Luca (QM DI AID) : I Received an answer, however i sadly cant review the users reply with the link
Patena Edwin Nalupa (BE QM MAL CQE 1) | Provide count of >1 case | FAR cases containing “PG-VQFN-48-31 | https://quai-deploy-web-uat-quai-development.ap-sg-1.icp.infineon.com/chat/d7d2d40e-e70e-48e2-bc04-2da87b315510 | System Bug? | yes |  |  | Reckemeyer Luca (QM DI AID) : Different reply than before for more or less same question. Why no quantity given?
Patena Edwin Nalupa (BE QM MAL CQE 1) | Provide FAR cases of >1 | count of FAR cases containing “PS 8D Preliminary Assessment Score of 94.29 | https://quai-deploy-web-uat-quai-development.ap-sg-1.icp.infineon.com/chat/37a5f0e5-5f37-469d-961a-9434b91afa0e | Enhancement | yes (if applicable?) |  |  | Reckemeyer Luca (QM DI AID) : I think assessment score is not included currently
Patena Edwin Nalupa (BE QM MAL CQE 1) | Provide count of >1 case | Count the FAR cases that contain the word "Focus" | https://quai-deploy-web-uat-quai-development.ap-sg-1.icp.infineon.com/chat/18b27fe5-0873-4a0e-9a58-fe2b322ad7d4 | Enhancement | yes |  |  | Reckemeyer Luca (QM DI AID) : Cant review user actual feedback through link. I received a case number >1 (but still seems too small, no time period specified?) Would it also be possible without defining where (in which column) to find the information "Focus", "Baseline" etc.? (Would normally be "Complaint Category")
Patena Edwin Nalupa (BE QM MAL CQE 1) | Special Cause | PS Problem category for CMA 825081050001 | https://quai-deploy-web-uat-quai-development.ap-sg-1.icp.infineon.com/chat/401a90d8-54bc-46d0-a2ee-8c1d01ed2204 | Inaccurate question? | yes |  |  | Reckemeyer Luca (QM DI AID) : Wrong User expectation? Why would you expect "Special cause" if you ask for PS Problem category? "Special Cause" would be related to the "Complaint Category" column. If instruction unclear, maybe advice the user to clarify.
Teh Pei Ning (BE QM MAL CQE 2) | FA result or FA link | Please give me FA result for 826020712? | https://quai-deploy-web-uat-quai-development.ap-sg-1.icp.infineon.com/chat/ff1f43b0-d530-44af-a491-5ba33f1d1d1e | Enhancement | yes |  |  | Reckemeyer Luca (QM DI AID) : Expectation to be clarified, cant review users actual answer through link. Result received:
Teh Pei Ning (BE QM MAL CQE 2) | To get corrective action and preventive action | Please give me CAPA for 826020712? | https://quai-deploy-web-uat-quai-development.ap-sg-1.icp.infineon.com/chat/ff1f43b0-d530-44af-a491-5ba33f1d1d1e | Enhancement | yes |  |  | Reckemeyer Luca (QM DI AID) : CAPA (Corrective and preventive Action) not included currently
Teh Pei Ning (BE QM MAL CQE 2) | To get correct info for origin of defect, package, incoming date | Please share me origin of defect, package, incoming date for 826020712 | https://quai-deploy-web-uat-quai-development.ap-sg-1.icp.infineon.com/chat/ff1f43b0-d530-44af-a491-5ba33f1d1d1e | System Bug? | yes |  |  | Reckemeyer Luca (QM DI AID) : Cant review users actual answer; Result received:

## Screenshots
Image 1 — referenced from 'Testing Status'!I7