## Testing Status
Pilot User | Prompt / Query | Actual Output | Expected Information | Categorization | Will it be Implemented ? (Inputs from the Usecase owner) Wong Wendy (QM QSC QQ) | Implementation Status | IT Comments
de La Cruz Emelyn (QM QSC) | Please advise the MSL and net weight of IPT65R040CFD7 | Net weight: two values are provided in the data – 65.0 mg and 774.0 mg | MSL 1 net weight 774mg | Enhancements (Logic Revisements) | yes | completed | new product logic applied (material status ==undefined and pre-m9 == No to get final results)
de La Cruz Emelyn (QM QSC) | Give me the product information of TLE4986C-XTS-M47 | Wafer Fab Loc = No data | PGS+ = 7A (Infineon Technologies Kulim, Malaysia ) & RG (Infineon Technologies Regensburg, Germany) | Enhancements (additional data required) | yes | completed | add wafer fab loc 2
de La Cruz Emelyn (QM QSC) | give me the max storage period in days and MSL level and net weight and division and QRC of products 1. CYPD7192-39BFXS 2. TLE9104SH 3. TLF51801ELV 4. BSS84P H6327 5. IPZ40N04S5L-4R8 | multiple values in BSS84P H6327 and IPZ40N04S5L-4R8 | PGS+ shows only 1 value per each products 1. CYPD7192-39BFXS = 730days 2. TLE9104SH = 1095 days 3. TLF51801ELV = 1095 days 4. BSS84P H6327 = 1095 days 5. IPZ40N04S5L-4R8 = 1095 days | Enhancements (Logic Revisements) | yes | completed | new product logic applied
de La Cruz Emelyn (QM QSC) | Give me the MSL level, net weights, divisions and QRC of products 1. CYPD7192-39BFXS 2. TLE9104SH 3. TLF51801ELV 4. BSS84P H6327 5. IPZ40N04S5L-4R8 | Re-test the same information from 7-May but no information record shows on 11-May, 2026 | Mutiple informations | System bugs | yes | completed | bug fixed by optimizing the text2sql prompt -- fixed, new reply https://quai-deploy-web-uat-quai-development.ap-sg-1.icp.infineon.com/share/eac84154-e117-48ec-9de3-312a181a83b7E"""
de La Cruz Emelyn (QM QSC) |  | For multiple parts, it usually comes into blank, see sreen shot at the right. Then have to refresh to show the data. |  | Enhancements (Logic Revisements) | yes | completed | updated, able to search across multiple tables
Lee Yee Vee (QM QSC) | how about the process node in nm for S29GL256S10TFI010? | For product S29GL256S10TFI010, the process node (minimum feature size) is not available in the data provided. | 65nm | Data Discrepancy (data missing) | yes | completed | some values in process node in DEAL are NULL (process line → min feat size) [Screenshot: see "Screenshots" sheet, Image 1] the data in 'process group'→'descr' is not of good data quality -- update: currently for the products with null technology node, no reliable attribute to replace them
Lee Yee Vee (QM QSC) | technology and node for TLE9877QXA40 | not able to provide process node | 0.13um/130nm | Data Discrepancy (data missing) | yes | in progress | values in process node are all NULL, pending to fix -- update: currently for the products with null technology node, no reliable attribute to replace them when user asks for 'technology', provide 'process group' and 'process technology'
Lee Yee Vee (QM QSC) | package name and PL for 3IDDB2U20N12W1_B22_A | it not able to seach, but this part is availble in PGS+ |  | Data Discrepancy (data missing) | no | completed | RC found, 3IDDB2U20N12W1_B22_A is a ‘AZ product’ (sample) -- 3IDDB2U20N12W1_B22_A is also a ‘AZ product’ (sample) and doesn’t own a structure. That’s why it’s not in vertical structure table.
Lee Yee Vee (QM QSC) | what is the die thickness of IAUCN04S7N005 | The provided answer based on raster Y is wrong, it should be 65 µm (DEALS) | 65 µm | Enhancements (additional data required) | yes | completed | new field added. correct value provided
Konda Sai Srikar Reddy(QM QSC) | Could you please give Fab/Assembly/Test location information? BGSX 33M5U16 E6327 BGS 14M8U9 E6327 BGS 14WMA9 E6327 BGS 15MU14 E6327 BGSX 24MU16 E6327 BGSX 24M2U16 E6327 BGSX 44MU18 E6327 BGSA14GN10 E6327 | Everything correct except for the BGS 14M8U9 E6327 where it missed out 5H as the assembly location and for BGSX 24M2U16 E6327 it missed out DM as a assembly location and for BGSX 44MU18 E6327 it missed out MA as an assembly location and DD as a wafer fab location | • BGS 14M8U9 E6327 5H as the assembly location • BGSX 24M2U16 E6327 DM as a assembly location • BGSX 44MU18 E6327 MA as an assembly location and DD as a wafer fab location | Data Discrepancy (data missing) | yes | completed | AZ Product/Doesn't have complete DEAL Structure)
Konda Sai Srikar Reddy(QM QSC) | "please help provide DPS368 Manufacturing location thx" | Provided the correct location but needs to be city, country format(Customer always needs country)-COA COD | "Assembly location and final test: W3 Wafer fab/test location: RG DD VI" | Enhancements (Output Formatting) | yes | completed | right format provided
Konda Sai Srikar Reddy(QM QSC) | What is the final wafer thickness for SP005569114 | QUAI cannot find the thickness but Final wafer thickness available in deal | 65µm | Enhancements (additional data required) | yes | completed | new field added. correct value provided
Konda Sai Srikar Reddy(QM QSC) | "Give date of mass production for the following part numbers: Q6223-B0-WT170AA-A000 Q3244-A3-WT110AA-A000" | Mass production date avaliable in PGS+ but QUAI says not available | "12/2025,02/2026" | Enhancement (Term Definition) | yes | completed | update term definition, correct value provided
Lee Yee Vee (QM QSC) | COD for CY8C4024LQI-S412T and CY8C4025LQI-S411 | not able to provide | COD: USA/Singapore | Enhancement (Term Definition) | yes | completed | add COD description in the agent, correct value provided
Lee Yee Vee (QM QSC) | who is the BLQM/QM contact for BCV 61C E6327 ? | not able to provide | Braun Elmar (PSS QM RF COM) | Out of Scope | no | Out of scope | PII, not provided
Konda Sai Srikar Reddy(QM QSC) | What is the marketing contact for 88Q1010-B0-NYA2A000-P123 | not able to provide | Choudhry Salil (ATV ES M) | Out of Scope | no | Out of scope | PII, not provided
Konda Sai Srikar Reddy(QM QSC) | Is ISC016N04NM7V Halogen free? | not able to provide | Yes | Enhancements (additional data required) | yes | completed | new field added. correct value provided
Lee Yee Vee (QM QSC) | what is the active SP# for BCV 61C E6327? | not able to provide | SP000010887 | although discontinue for ordering but product still need to deliver for fulfillment | yes | completed | updated bussiness logic. new reply "For BCV 61C E6327, the SP# in the database is SP000010887 (Product Status: discontinued)."
Konda Sai Srikar Reddy(QM QSC) | Is IPB330P10NM completely Lead free | not able to provide | No | Enhancements (additional data required) | yes | completed | new field added. correct value provided
Konda Sai Srikar Reddy(QM QSC) | What is the HFGR of PXE1110CDM-G003 | not able to provide | P | Enhancements (additional data required) | yes | completed | new field added. correct value provided
Konda Sai Srikar Reddy(QM QSC) | What is the small packing unit value for S25HL02GTDPBHV053 | not able to provide | 2000 | Enhancements (additional data required) | yes | completed | new field added. correct value provided
Konda Sai Srikar Reddy(QM QSC) | What is the large packing unit of TLE4271-2G | not able to provide | 1000 | Enhancements (additional data required) | yes | completed | new field added. correct value provided
Konda Sai Srikar Reddy(QM QSC) | What is the SAP MATNR for BSS84PW H6327 | not able to provide | PG-TLGA-5/U9922/Y/_/_ | Enhancement (Term Definition) | yes | completed | update term definition, correct value provided
Konda Sai Srikar Reddy(QM QSC) | What is the variant characteristic for BSS806NE H6327 | Unable to pull out information | FE KUL, BE Wuxi,FE Kulim, BE Wuxi; Recovery of plating Welnew Wuxi,PB FREE; SN 11um NOM; Halogen free, CU wire, BE Wuxi,PLATING WELNEW; PB FREE; SN 11um NOM; Halogen free, CU wire, BE Wuxi,Recovery of plating Welnew Wuxi,Welnew Shanghai | Enhancements (additional data required) | yes | completed | variant_descr added, new reply """ For BSS806NE H6327, the variant description values are: • FE Kulim, BE Wuxi; Recovery of plating Welnew Wuxi • PB FREE; SN 11um NOM; Halogen free, CU wire, BE Wuxi • PLATING WELNEW; PB FREE; SN 11um NOM; Halogen free, CU wire, BE Wuxi • Recovery of plating Welnew Wuxi"""
Lee Yee Vee (QM QSC) | die size of IMYR140R006M2H | For product IMYR140R006M2H, the die sizes are: • 3.65 × 6.31 • 6.31 × 3.65 | Chip Size (X*Y)= 3.65mm * 6.31mm | No Further Action Required | no | No action required | comfirmed with user, product bot provide right response - no action
Lee Yee Vee (QM QSC) | package name and pic no for BSC146N10LS5 | pic no is available in DEAL+PD (Test Mark Assd Chips>Marking Patterns) | "Package name: PG-TDSON-8-45 Pic no: 1" | Enhancements (additional data required) | yes | completed | new field added. correct value provided new reply """ For BSC146N10LS5, the package name and PIC No are: • Package Name: PG-TDSON-8-45 • PIC No: 1"""
Konda Sai Srikar Reddy(QM QSC) | Marking format for BSC320N20NS3 G | no 'marking format' | For product BSC320N20NS3 G, the available marking format links are: • https://goto.infineon.com/pck-completion?package=PG-TDSON-8-50 • https://goto.infineon.com/pck-completion?package=PG-TDSON-8-46 • https://goto.infineon.com/pck-completion?package=PG-TDSON-8-7 | Enhancements (additional data required) | yes | completed | new field added. correct value provided added, new reply """ For BSC320N20NS3 G, the marking format URLs are: • https://goto.infineon.com/pck-completion?package=PG-TDSON-8-50 • https://goto.infineon.com/pck-completion?package=PG-TDSON-8-46 • https://goto.infineon.com/pck-completion?package=PG-TDSON-8-7"""
Lee Yee Vee (QM QSC) | Test temperature of IPD50P04P4-13 | Unable to pull out information | "Wafer Test: 25c Final Test: 25c" | Enhancements (additional data required) | yes | completed | new field added. correct value provided, new reply: For IPD50P04P4-13, the test temperatures are: • Wafer test temperature (BE): 25.0 • Final test temperature (FE): 25.0"""
Law Mooi Sim (QM QSC) | please support for MSL/max storage days for part ICE3BS03LJG | "given 3 values for the max storage days: MSL 3 with max storage 1095 days MSL 3 with max storage 365 days MSL 3 with max storage 730 days" | "MSL 3 Max storage days: 1095" | Enhancements (Logic Revisements) | yes, | completed | new logic added, correct value provided new reply """ For ICE3BS03LJG, the moisture/reliability details are: • MSL (Moisture Sensitivity Level): 3 • Max Storage Days: 1095.0"""
Law Mooi Sim (QM QSC) | "Give me the process technology for the following parts: BTS7012-2EPG TLF11251LD TLF35584QVVS1 SAK-TC397XP-256F300S BD TLE42664G KP467" | multiple values provided for TLE42664G, "TLE42664G: DOPL4_8, DOPL_6"" | "BTS7012-2EPG: SMART7_12 TLF11251LD: SPT9_65V_8 TLF35584QVVS1: SPT9_65V_12, SPT9_65V_8 SAK-TC397XP-256F300S BD: C40FLA TLE42664G: DOPL4_8 KP467: SPT9_P8" "PGS+ shows only 1 value for this part: TLE42664G" | Enhancements (Logic Revisements) | yes | in progress | Updated: To provide process technology and process group both.
Law Mooi Sim (QM QSC) | "Support for technology node & Process technology for the following parts: BTS7012-2EPG TLF11251LD TLF35584QVVS1 SAK-TC397XP-256F300S BD TLE42664G KP467" | not able to provide | "BTS7012-2EPG: 0.35 µm TLF11251LD : 0.13 µm TLF35584QVVS1: 0.13 µm SAK-TC397XP-256F300S BD: 40 nm TLE42664G: 3 µm KP467: 0.13 µm" | Data Discrepancy (data missing) | yes | completed | values in process node are all NULL, pending to fix -- update, the process node for these products are updated (Provide 2 data: Process node, and process technology)
Law Mooi Sim (QM QSC) | give me the shelf life/MSL of this part: BTF3050TE & SN7002N H6327 | given multiples answer | "BTF3050TE MSL=1 Shelf life=1095 days SN7002N H6327 MSL=1 Shelf life=1095 days" | Enhancements (Logic Revisements) | yes | completed | new logic added, correct value provided (Pre-m9 and material status logic included)
Law Mooi Sim (QM QSC) | "We have a customer inquiry regarding BAT60AE6327HTSA1 and would like to request confirmation on the following items: FAB Site Could you please confirm the wafer fabrication site for this device? Assembly Site Could you please confirm the assembly site for this device? Mass Production Start Timing Could you please advise the mass production start timing for this device?" | given all the M9 released date and inactive baunumber & Pre-M9 locations | "FAB Site: Infineon. Villach, Austria Assembly Site: Infineon, Wuxi, China Mass Production Start Timing: April/2001" | Enhancements (Logic Revisements) | yes | competed | Pre-m9 and material status logic included -- new reply " For BAT60AE6327HTSA1, the requested manufacturing sites and mass production start timing are: • Wafer Fab Site: VI — Infineon Technologies Villach, Austria • Assembly Site: WX — Infineon Technologies Wuxi, China • Mass Production Start Timing (M9 Release Date): 2001-04-27"
Law Mooi Sim (QM QSC) | give the msl & shelf life for these 2 parts: S25FS064SAGMFM010 & S25FS064SDSMFM010 | "both part MSL=3, Shelf life = 3 years" | null for msl | Data Discrepancy (data missing) | yes | completed | -- verify by sql query "SELECT distinct msl1, MSTL_MSL, SALES_NAME FROM vdb_bl_md_product.bl_mdprd_mp_dset_qualytics_basic_information WHERE SALES_NAME in ('IPT65R040CFD7','S25FS064SAGMFM010','S25FS064SDSMFM010', 'CYPD7192-39BFXS', 'TLE9104SH', 'TLF51801ELV', 'BSS84P H6327', 'IPZ40N04S5L-4R8','2EDL5013U2D','2EDL900G3')" -- updated MSL with msl1 in data pipeline -- new reply https://quai-deploy-web-uat-quai-development.ap-sg-1.icp.infineon.com/share/1c57191f-741a-404c-8a1a-ae24f3b4480f
Law Mooi Sim (QM QSC) | "Give me the part 2ED2410-EM 1. Process technology 2. Process node/minimum feature size (nm) 3. Fab/Assembly/Test" | "-Min feature size/technology node is out of scope - when ask for mfg loacation need to spcified afater M9 released, else giving all the pre-9 location." | Process technology Process node/minimum feature size ( Wafer Fab Location (Kulim, Malaysia/VIS, Taiwam) Assembly location (Melaka, Malaysia) Test location (Batam, Indonesia) | Data Discrepancy (data missing) | yes | completed | values in process node are all NULL, pending to fix -- update: the process node data in DEAL is updated, now can get '1.2 µm' for process node
Linh Asley (PSS QM AP) | What is the country of original for the part TDM22544D? | We want to know the assembly location (COO) but the result showing Wafer FAB location. | The result should be showing country of original for this part is Vietnam | Enhancement (term definition) | yes | completed | For this product, assembly location is AT&S Loeben, Austria, there is no Vietnam found. To take from vdb_bl_sc_logistics.bl_sclog_onetm_biz_batches_cross_plants_transpose SELECT vdb_bl_sc_logistics.bl_sclog_onetm_biz_batches_cross_plants_transpose."COO" AS "COO" FROM vdb_bl_sc_logistics.bl_sclog_onetm_biz_batches_cross_plants_transpose WHERE "LOTNUMBER" = 'ZA511015WA3'
Huang Ying (CSS OP QM 1)) | where is backend for VSTD1313 WLB16, this is for POM | not able to provide | Show wafer site for this DSI part | Data Discrepancy (data missing) | yes | in progress | can't find VSTD1313 WLB16 in db, checking the data issue -- RC found, but if applying the filter, downstream fact table will be affacted. further investigation required. -- Waiting Update from data team (Assuming DWHINT is fixed by 24 July, data team will start by 27 July, 8 August is end of the sprint)
Choy Wai Meng (ATV QM CQS CQM AP) | Where are the backend assembly and test sites for TLE75008-ESD with lot number 1E205624Q11 ? | not able to provide | Assembly location and backend final test sites for the specified lot nr | Out of Scope | no | out of scope | lot number not provided in product table
Cabuhat Cynthia (PSS QM QES) | Where is the Back-End site for IPT017N12NM6? | "First prompt using the same sentence: fail Secon promt using the same sentence : pass" | "Correct: For product IPT017N12NM6, the Back-End site (assembly and final test) is: Assembly location: ML – Infineon Technologies Melaka, Malaysia Final test location: ML – Infineon Technologies Melaka, Malaysia" | Enhancements (term definition) | yes | completed | add term definition for backend site (including assembly location and final test location)
Cabuhat Cynthia (PSS QM QES) | How many chips are inside TDA22594A ? | not able to provide | Answer is 3 Chips 1 in PGS+ [Screenshot: see "Screenshots" sheet, Image 2] | Enhancements (additional data required) | yes | completed | new attribute required (chip number) - this data is part of product attribute Update: quantity of chips added
Cabuhat Cynthia (PSS QM QES) | Please show me the bonding diagram of TDA22594A | not able to provide | Connect to Deal+PD to get the Bonding Diagram | Enhancements (additional data required) | yes | in progress | bonding diagram - common request from customers Update: For some products (e.g. TDA22594A) that doesn't have assembly chips, the “delved” for bonding diagram are unviable in bl_mdprd_mp_dset_qualytics_bom_data, although the bonding diagram can be found in DEAL+PD
Cabuhat Cynthia (PSS QM QES) | "Tool hanged . Error chronology: 1. I asked how many chips are inside TDA22594A ? Tool cannot give the exact answer but suggested that it can give other info like BOM, etc. 2. I wrote ""ok .."" in the prompt and the tool showed something and then it hanged" | not able to provide | If the tool is offering alternative option, it shout show it when the user prompt "yes", or "yes, please show me" or similar affirmative prompt. | System bugs | yes | in progress | memory issue to address To further investigate Rajadurai Sudhan (IT SBI BIA CCA / External)
Tanno Toshiaki (PSS QM JP) | Package type for PMC41430 | PG-IQFN-39-17 | "QUAI answer: For product PMC41430, the package type is TAPE & REEL. Propose to change wording: ""Package type"" or ""Packaging type"" = ""Packing type"" or ""Packing style"". ""Package Name"" such as TO247, VQFN, etc. = no change" | Enhancements (Logic Revisements) | yes | completed | Update: For PMC41430, the package name is PG-IQFN-39-17. Require a explanation about following attributes and their difference Package type Packaging type Packing type Packing style Package name
suharni | Pls provide the various available SP# and the whole customers names buying the SLE956681-0007 TSNP6? | not able to provide | I expect that the product SP # to be given SP005934261; data not found in Product Agent? | No further action required | no |  | Use shipment bot for this type questions. this query is related to Shipment, use shipment agent for reply: https://quai-deploy-web-uat-quai-development.ap-sg-1.icp.infineon.com/share/bee44511-be48-406a-bef0-f260cb3a7c8a
Suharni | "Continue .. where are manufacturer plant of this part ?" previous question: what is the basic type of SLE956681-0007 TSNP6 | "Instead they ask me to provide a specific product identifier (for example sales name/part number, MA number, SP number, basic type, BAU number, OPN, package name, or process group) so I can look up the manufacturing plant locations for you? Only 1 SP# if they were to check, hencve they coudl easily provide me thi info " | "FE: Dresden BE: UTL" | Enhancement (Term Definition) | yes | completed | "fixed, new reply """"""For this part, the manufacturing plants (front-end and back-end) are: Wafer fabrication (front-end): Infineon Technologies Dresden, Germany – Dresden, Germany Assembly (back-end): UTAC UTL1, Thailand – Bangkok, Thailand Final test (back-end): UTAC UTL3 Chachoengsao, Thailand – Chachoengsao, Thailand"""""""
Suharni | Continue… pls provide the respective MA# and sold to # for all the customers buying this parts ? | AI asked for more questions. If AI to check, only 1 SP# available. | my initial questions was wherea re they manufacturere .. But they ask me to give SP #, when there is only 1 SP# | No Further Action Required | no |  | cannot find this query in chat history https://quai-deploy-web-uat-quai-development.ap-sg-1.icp.infineon.com/share/86646376-275c-47e1-8bc4-002b4a495957 and the response in the chat history, response """I'd be happy to help! This question is about shipments/customers, so please switch to the Shipment Bot for assistance with MA# and sold-to# details.""" - Customers not available in PGS+DEAL, it is TMA data -- To use shipment bot
Suharni | what is the basic type of CYBT-413061-02 and how many ICs are in this module? | not able to provide | H3003A, Qualytics able to provide the basic type for this BLE module | Enhancements (additional data required) | yes | completed | Update: new attribute (# of IC) added New reply: For CYBT-413061-02, the Basic Type is H3003A, and the module has 5879 ICs (chips per wafer). • Basic Type: H3003A • ICs in this module (Chips per Wafer): 5879.0
Suharni | "Continue.. what is the basic type of CYBT-413061-02" | not able to provide | "H3003A If u were to check , there's only 1 SP and 1 MA " | Enhancements (Logic Revisements) | yes | completed | Provide single basic type now, new response """For product CYBT-413061-02, the basic type is H3003A."""
Suharni | "Continue.. where are they manufacture?" | not able to provide | "Wafer Fab Loc None, TSMC_TW_Fab14 Wafer Test Loc None, TSMC_TW_Fab1 Assembly Loc SPIL_TW Final Test Loc WSJ_CN" | Enhancement (Term Definition) | yes | completed | updated, new response """""" For CYBT-413061-02, the manufacturing locations are: Location Name Wafer Fab ¦ 84 ¦ TSMC Fab14 Tainan, Taiwan Wafer Test ¦ 84 ¦ TSMC Fab14 Tainan, Taiwan Assembly ¦ 2N ¦ SPIL Taichung, Taiwan Assembly ¦ XU ¦ ASE Kaohsiung, Taiwan Final Test ¦ 45 ¦ Wujiang Sigmatron Electronics Co., Ltd., Jiangsu, China """""""
Konda Sai Srikar Reddy(QM QSC) | What is the final wafer thickness of IAUCN04S7N005 | not able to provide | 65u | Enhancements (additional data required) | yes | completed | die thickness added.
Konda Sai Srikar Reddy(QM QSC) | Is there ROHS compilance for 88Q1110-B0-NYA2A000 | not able to provide | Yes | Enhancements (additional data required) | yes | completed | ROHS added.
Konda Sai Srikar Reddy(QM QSC) | "What is the Marking Format of 2EDN1153DAA" | not able to provide | Marking Format | Enhancements (additional data required) | yes | completed | marking format added
Konda Sai Srikar Reddy(QM QSC) | What is the die thickness of IQEH46NE2LM7ZCGSC | not able to provide | die thickness | Enhancements (additional data required) | yes | completed | die thickness added
Konda Sai Srikar Reddy(QM QSC) | What is the final test temperature of TLS850C2TE V33 | not able to provide | final test temperature | Enhancements (additional data required) | yes | completed | final test temperature added
Ivy Lim (QM QSC) | please provide the wafer diameter of IAUCN04S7N012 | not able to provide | 300mm | Enhancements (additional data required) | yes | completed | Update: wafer diameter unit added New reply: For product IAUCN04S7N012, the wafer diameter is 300.0 mm.
Ivy Lim (QM QSC) | please provide the product information for IRF9Z34NPBF, which has already been released and is currently above M9? Please exclude any End-of-Life (EOL) or discontinued parts from your response. | "QUAI cannot filter for both ""active"" and ""M9 product"" simultaneously. The system can filter to show only M9 and active products." |  | No Further Action Required | no | no further action required | Confirmed with user, not further action required (UI can select multiple filters).
Ivy Lim (QM QSC) | please provide the CTE value of IRF9Z34npbf | not able to provide | CTE value | Enhancements (additional data required) | yes | competed | Update: CTE added New reply: For IRF9Z34NPBF, the CTE values are: • CTE Value 1: 17 ppm/ degreesC; CTE Value 2: 60 ppm/ degreesC • CTE Value 1: 14 ppm/ degreesC; CTE Value 2: 61 ppm/ degreesC
Ivy Lim (QM QSC) | ESD (CDM,HBM) | not able to provide | CDM: C3 ( >= 1000 V ) HBM: 2 ( 2000 V to < 4000 V ) | Enhancements (Logic Revisements) | yes | completed | "response: ""For product IPP029N15NM6, the ESD classifications are: CDM: C3 ( >= 1000 V ) HBM: 2 ( 2000 V to < 4000 V )"""
Ivy Lim (QM QSC) | Give me the glass temperature of IRF9Z34npbf | not able to provide | glass temperature | Enhancements (additional data required) | yes | completed | Update: glass transition temperature added New reply: For product IRF9Z34NPBF, the glass transition temperature (Tg) values are 160 °C and 175 °C. • 160 °C • 175 °C
Ivy Lim (QM QSC) | solder wire of IRF9Z34npbf | not able to provide | solder wire | Enhancements (additional data required) | yes | completed | solder wire to add
Ivy Lim (QM QSC) | what is the mass production date of IRF9Z34npbf | not able to provide | 1/6/2016 (filter only bau= 99 and status =9 filtering by BAU number 99 and QA Status = S, the first date displayed is the Mass Production (MP) day | Enhancements (logic revisement) | yes | completed | -- new business logic added: show the earliest date from Material Status=LOCK with M9 (S) (QA status=S means it reached M9)
Ivy Lim (QM QSC) | QM contact of IRF9Z34npbf | not able to provide |  | Out of Scope | no | Out of scope | PII, not provided
Ivy Lim (QM QSC) | give me the dimension of mmb bag of 1EDI2002AS | not able to provide | dimension of mmb bag | Enhancements (additional data required) | yes | completed | dimension of mmb bag to add
Ivy Lim (QM QSC) | what is the marking format of IQEH46NE2LM7ZCGSC | not able to provide | marking format | Enhancements (additional data required) | yes | completed | marking format added
Ivy Lim (QM QSC) | please give me the tape and reel dimension of IAUCN04S7N012 | not able to provide | tape and reel dimension | Enhancements (additional data required) |  | completed | tape and reel dimension to add
Ivy Lim (QM QSC) | please give me the shipping box dimension of IAUCN04S7N012 | not able to provide | shipping box dimension | Enhancements (additional data required) |  | completed | shipping box dimension to add
Li Kevin (PSS QM GC) | For the product IPTC014N10NM5, pls show me the POD dimension (package of dimension) from different assembly site? | not able to provide | different POD drawings from differnt assembly site | Enhancements (additional data required) | yes | completed | package of dimension to add
Li Kevin (PSS QM GC) | What's the FE fab location for the lot # ZF501236G20? | not able to provide | Wafer fab location based on the given lot number. | Out of Scope | no | Out of scope. | PGS no lotnumber lot # not available in product table
de La Cruz Emelyn (QM QSC) | Please advise the MSL and net weight of IPT65R040CFD7 | For product IPT65R040CFD7, the requested information is: • MSL (Moisture Sensitivity Level): 1.0 • Net weight: two values are provided in the data – 65.0 mg and 774.0 mg | "MSL 1 net weight 774mg" | Enhancements (logic required) | yes | completed | Done: Include the pre-m9 and material status business logic in the response to ensure the same data as expection. new response """For product IPT65R040CFD7, the requested information is: MSL (Moisture Sensitivity Level): 1 Net Weight: 774.0 mg"""
de La Cruz Emelyn (QM QSC) | Give me the product information of TLE4986C-XTS-M47 | Wafer Fab Loc = No data | PGS+ = 7A (Infineon Technologies Kulim, Malaysia ) & RG (Infineon Technologies Regensburg, Germany) | Enhancements (additional data required) | yes | completed | wafer fab loc 2 added, new response """Wafer Fab Loc: 7A; RG Wafer Fab Loc Name: Infineon Technologies Kulim, Malaysia; Infineon Technologies Regensburg, Germany"""
de La Cruz Emelyn (QM QSC) | please provide the BOM of TLE4986C-XTS-M47 | "1. Die Attach Name: not specified in the data but the rest information are correct " | Mutiple informations | Enhancements (additional data required) | yes | completed | Die Attach Material added
de La Cruz Emelyn (QM QSC) | "give me the max storage period in days and MSL level and net weight and division and QRC of products 1. CYPD7192-39BFXS 2. TLE9104SH 3. TLF51801ELV 4. BSS84P H6327 5. IPZ40N04S5L-4R8" | multiple values | "PGS+ shows only 1 value per each products 1. CYPD7192-39BFXS = 730days 2. TLE9104SH = 1095 days 3. TLF51801ELV = 1095 days 4. BSS84P H6327 = 1095 days 5. IPZ40N04S5L-4R8 = 1095 days " | Enhancements (Logic Revisements) | yes | completed | Done: Logic is added (material status ==undefined and pre-m9 == No to get final results)
Pralhad Kulkarni | can you provide me more details on PG-VQFN-32-20 | details not fetched |  | System bugs | yes | completed | fixed
Pralhad Kulkarni | For product ISC018N08NM6, pls show me the global FAR history overview, any confirmed valid IFX caused issue? |  |  | No Further Action Required | no | No further action required | wrong conversation link from feedback, "Give me the product information of SLJ22CSA1M8T1", and this query should go to far agent, response: https://quai-deploy-web-dev-quai-development.ap-sg-1.icp.infineon.com/chat/59b63848-c706-4999-8a55-87a570e10dc9
Maggie Chen | what is the Q status of XDP720-001? | not able to provide |  | Enhancements (additional data required) | yes | completed | q-status to add, is it the same as QA-status? - Yes -- update: QA-status added, new reply """For XDP720-001, the Q status (QA Status) is S."""
Maggie Chen | what is the price of BGA 824N6 E6329 in ISAR? | not able to provide | Price which can be used for FAR shipment | Enhancements (additional data required) | no | Out of scope | price to add, and what is ISAR? - this is Sales topic, ISAR is Sales platform for samples ordering
Maggie Chen | which test location is for site code 38? | not able to provide | TFME | Enhancements (term definition) | yes | completed | "fixed, new response """"""For site code 38, the final test location is: Final Test Loc: 38 Final Test Loc Name: TFME TongKe, China"""""""
Pei Phoebe (PSS QM GC SHA) | what's the release date, weight, CO2 emission factor, die size, bonding wire material, ESD(HBM) class, MSL level for 2EDL5013U2D? | "M9 release date, MSL level provided. But no information for: -weight -CO2 emission factor -die size -bonding wire material -ESD(HBM) class," | all info | Enhancements (additional data required) | no | No further action required (CO2 out of scope) | CO2 emission factor - CO2 is Sustainability topic, provided by MatQ (Material Query team)
Pei Phoebe (PSS QM GC SHA) | what's the MSL level for 2EDL900G3? | "No MSL level provided, but there is MSL information in https://www.infineon.com/part/2EDL900G3" | 1 | Enhancements (additional data required) | yes | completed | fixed
New Pilot Users 05 Aug 2026

## No Further Action
Pilot User | Prompt / Query | Actual Output | Expected Information | Categorization
Konda Sai Srikar Reddy(QM QSC) | What is the serial number (serial no.) of BSR92P H6327. | not able to provide | F003,F0016,F0021,F0019 | No Further Action Required
Konda Sai Srikar Reddy(QM QSC) | What is the V-SNR of BSR92P H6327 | not able to provide |  | No Further Action Required
Konda Sai Srikar Reddy(QM QSC) | Is the structure created for BSR92P H6327 | not able to provide | Yes | No Further Action Required
Konda Sai Srikar Reddy(QM QSC) | Is there rework flag for PSC3M5FDS2ACQ1 | not able to provide | No | No Further Action Required
Konda Sai Srikar Reddy(QM QSC) | What is the SAP MATNR plant status for MA006083832 | not able to provide | PP | No Further Action Required
Konda Sai Srikar Reddy(QM QSC) | What is the SLOC SAP Storage location of 88Q5050-B0-LKJ2A000 | not able to provide | 0500 | No Further Action Required
Konda Sai Srikar Reddy(QM QSC) | What is the PIO material group of BAT 64-02V H6327 | not able to provide | I9A00 | No Further Action Required
Konda Sai Srikar Reddy(QM QSC) | What is the MD process for BSS84PW H6327 | not able to provide | IFX | No Further Action Required
Konda Sai Srikar Reddy(QM QSC) | What is the main product group for IPW60R120CM8 | not able to provide | E | No Further Action Required
Konda Sai Srikar Reddy(QM QSC) | Who is the supply chain planner for CY7C1041G30-10BAJXET | not able to provide | RH | No Further Action Required
Konda Sai Srikar Reddy(QM QSC) | What is the PPOS for IPD50N04S4L-08 | not able to provide | IPD50N04S4L-08C | No Further Action Required
Konda Sai Srikar Reddy(QM QSC) | What is the FPOS for IR38062MTRPBF | not able to provide | 2 | No Further Action Required
Konda Sai Srikar Reddy(QM QSC) | QA status for TDA21598 | not able to provide | K,V | No Further Action Required
Konda Sai Srikar Reddy(QM QSC) | What is the cost unit for BSC320N20NS3 G | not able to provide | 51 | No Further Action Required
Konda Sai Srikar Reddy(QM QSC) | Is SAK-TC337LP-32F300S AA Tested with ROM flag | not able to provide | No | No Further Action Required

## Screenshots
Image 1 — referenced from 'Testing Status'!H7
Image 2 — referenced from 'Testing Status'!D41