## Testing Status
Pilot User | Prompt / Query | Actual Output | Expected Information | Categorization | Should it be Implemented ? (Inputs from the Usecase owner) Reckemeyer Luca (QM DI AID) | When will be implemented? (Alignment with IT) | Comments
Johanna Ocklenburg | How many devices of SAK-TC397XP-256F300S BD were shipped in April 2026? | Your request has timed out due to the large volume of records matching your query. Please refine your search criteria | Shipment volume | System bugs | yes | completed | bug fixed, new answer: For product SAK-TC397XP-256F300S BD in the period 2026-04-01 → 2026-04-30, the total shipped quantity was 662,000 devices.
Klaus Fischer | assembly lot no for sales name TLE9877QXA40, datecode 2510 assembly code 22X? | no answer, loading since 10 min | one dedicated lot | Enhancements (Additional data required: assembly code) | yes | completed | loading issue fixed, response provided lot no for assembly lot no (are they the same?), but assembly code is not provided in db assembly codle
Ilona Wagner | give me all information you can find for this lot number: 82087370 | nothing it loaded forever | mat number, shipment number and so on | System bugs and Data Discrepancy (data missing) | yes | Out of scope | got screen shot from user, will check with the data team [Screenshot not included in the document – linked image: https://confluencewikiprod.intra.infineon.com/download/attachments/3490421721/image-2026-7-17_11-21-59.png?version=1&modificationDate=1784258519000&api=v2]
Choy Wai Meng (ATV QM CQS CQM AP) | "Who were the customers had received datecode 2230 for TLE75008-ESD ? What are the quantity shipped to each of these customers for this datecode 2230 ?" | Some customers not in the AI response and some quantity not correct as compared with TMA report | List of customer and quantity received in alphabetical order | Enhancements (Logic Revisement) | yes | completed | user use box datecode, currently we use lot datecode screen shot provided by user [Screenshot: see "Screenshots" sheet, Image 1] total quantity calculated by box datecode and lot datecode[Screenshot: see "Screenshots" sheet, Image 2] -- new business logic: use lot datecode, and to avoid misunderstanding with box datecode, add the word "lot" into the statement as "For product X with lot datecode YYWW......"
Pralhad Kulkarni | what product shipped to customer Aumovio in 2026 | Deep thinking for longer time no output generated |  | System bugs | yes | in progress | Timeout issue investigation • Agent execution flow • Dive time out performance • FE loading...
Maggie Chen | XDPP1100-Q024, all shipment record for customer Delta | no answer | shipment record | Enhancements(Output formatting) | yes | completed | exceed row limit, -- updated, new reply "The result set is quite large. You can find the complete shipment records for customer Delta (XDPP1100-Q024) in the data source for further analysis."
Maggie Chen | pls provide a list of all shipment for XDPP1100-Q024? | no answer | shipment record | Enhancements(Output formatting) | yes | completed | exceed row limit, fixed, new response """"""I can pull those shipment records, but I’ll need you to narrow it down a bit first" -- updated, new reply "The result set is quite large. You can find the complete data in the data source for further analysis."
Maggie Chen | check shipment record for IPW65R041CFD with datecode 2618 | no answer | some device has multi assemble and test location, in BO we can check such inform of specific lot, but QUAI cannot. | Enhancements (Additional data required) | yes | completed | assemble and test location to add to shipment table The filter based on specific lot can be done in the data source. It will list down all the records and allow further search and filter. The assembly and test locations are available in product bot
Pei Phoebe (PSS QM GC SHA) | shipment report for IPP039N10N5 within 1 year, contains lot number and ship to customer information | feedback no this part number IPP039N10N5 canbe found | shipment report for IPP039N10N5 | Enhancements(Output formatting) | yes | completed | fixed -- updated, new reply "The result set is quite large. You can find the complete shipment report data for IPP039N10N5 (past 1 year), including lot number and ship-to customer information, in the data source for further analysis."
New Pilot Users 05 Aug 2026
Salleh Syahrizal (BE QM QMS MT) | List all our customer and products they purchase from us | Could you please provide a specific identifier (e.g., a customer name/number or a product name/MA/SP number) so I can look up the customers and the products they purchased? I can return customer/ship-to details and product references from shipment records once you share one starting point. | List of all customers | Enhancement | yes |  | User: Data of customer is available Enhancement - Too much data?
Salleh Syahrizal (BE QM QMS MT) | Given a list of companies, identify if they are our customer - [AMD, Huawei, McDonalds] | No answer after 1 minute | Yes or no next to the company names | Enhancement | yes |  | User: A good lapse time should be within 20 seconds
Salleh Syahrizal (BE QM QMS MT) | Is AMD our customer? | • No answer after 1 minute • I’m not able to confirm specific customer relationships. I can help if you share the context (e.g., product line, region, or shipment/failure analysis reference). | Yes or no |  |  |  | User: A good lapse time should be within 20 seconds
Salleh Syahrizal (BE QM QMS MT) | list of products that we shipped to AMD | No answer after 1 minute | List of products |  |  |  | User: A good lapse time should be within 20 seconds Reckemeyer Luca (QM DI AID) : System bug, already mentioned by Pralhad Kulkarni - in progress
Salleh Syahrizal (BE QM QMS MT) | Return one product that AMD purchase from us | Your request has timed out due to the large volume of records matching your query. Please refine your search criteria. | Just one product, any one product that AMD purchase from us |  |  |  | User: Just pick any one product at random. Why does the system need to go through a large volume of record?
Salleh Syahrizal (BE QM QMS MT) | When was last shipment to AMD? | No answer after 1 minute | Latest shipment date |  |  |  | User: A good lapse time should be within 20 seconds
Salleh Syahrizal (BE QM QMS MT) | which customer purchase AUIRF3305 from us? | No answer after 1 minute | List of customer |  |  |  | User: A good lapse time should be within 20 seconds
Mohd Yusak Nur Fatihah (BE QM QMS) | which products under military export control? | I can’t help identify which specific products are under military export control, as that can involve regulated and sensitive compliance guidance. I’m an assistant designed to help with quality management queries including product information, shipment tracking, and failure analysis requests. https://quai-deploy-web-uat-quai-development.ap-sg-1.icp.infineon.com/chat/cb21d13f-2a84-4164-8f12-30a6b960f064 | List of part no

## Screenshots
Image 1 — referenced from 'Testing Status'!H5
Image 2 — referenced from 'Testing Status'!H5